## IHSRestServer
S.No | Task | Effort (in hours) | Status | Pending/Comments
1 | Jersey, Tomcat, Maven, Eclipse, Oracle 11g and related libraries - Installtion and Configuration | 4 | Complete
2 | Configuring Multi module Maven project - Recommended to use Eclipse Neon | 4 | Complete
3 | GsonProvider vs GensonProvider Evaluation, Hibernate configuration , Log4j | 6 | Complete
4 | POC with GsonProvider, Jersey, Maven, Hibernate, Oracle (Both ORM and Stored Procedure CRUD) | 6 | Complete
5 | Doctor CRUD | 1 | 50% | Get Consultation fee of selected Doc
6 | Department CRUD | 3 | Complete
7 | Patient CRUD | 4 | 70% | Test update, delete patient
8 | Appointment CRUD | 4 | 90% | Test cancel appointment
9 | Dao/Rest Api Test Cases - RestAssured Library | 4 | 30% | Patient, Doctor, Department Test cases to be done
10 | Oauth implementation using Apache Oltu | 8 | 30% | Integrate Rest Calls with Oauth Resource endpoint

## IHSPatientApp
S.No | Task | Effort (in hours) | Status | Pending/Comments
1 | Android Studio setup & configuration | 2 | Complete
2 | Retrofit setup and POC | 4 | Complete
3 | Layout XMLs for New Patient flow - Login, Registration, Appointment Home screen |  | Complete | Done by MSc Interns
4 | Database Design, DbHelper | 2 | Complete
5 | DateSerializer, DateDeserializer | 2 | Complete
6 | SyncAdapter | 10 | Complete
7 | Validation Library evaluation (Android saripaar vs custom Validation Library) | 2 | Complete
8 | Validation Setup, Utils | 6 | Complete
9 | EventBus - Otto (Evaluation Otto vs EventBus vs RxAndroid) | 6 | Complete
10 | Doctor CRUD | 2 | Complete
11 | MainActivity - Validation, CRUD | 3 | Complete
12 | MainActivity - ForgotOPCode - ForgotCredentialsActivity (ForgotOPCodeFragment) | 3 | Complete